## Raw Data
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11
Project Management | Project Manager | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 934 | 1016
Project Management | Project Manager | Plan (BAC) | R.14 - 9 Jun 25 |  | 934 | 934
Project Management | Project Manager | Plan (EAC) | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Project Manager | Actual | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Project Control Engineer (Planner) | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 934 | 1016
Project Management | Project Control Engineer (Planner) | Plan (BAC) | R.14 - 9 Jun 25 |  | 934 | 934
Project Management | Project Control Engineer (Planner) | Plan (EAC) | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Project Control Engineer (Planner) | Actual | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Cost Control | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 934 | 1016
Project Management | Cost Control | Plan (BAC) | R.14 - 9 Jun 25 |  | 934 | 934
Project Management | Cost Control | Plan (EAC) | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Cost Control | Actual | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Project Engineer | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 934 | 1016
Project Management | Project Engineer | Plan (BAC) | R.14 - 9 Jun 25 |  | 934 | 934
Project Management | Project Engineer | Plan (EAC) | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Project Engineer | Actual | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Document Control/Admin | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 934 | 1016
Project Management | Document Control/Admin | Plan (BAC) | R.14 - 9 Jun 25 |  | 934 | 934
Project Management | Document Control/Admin | Plan (EAC) | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | Document Control/Admin | Actual | R.14 - 9 Jun 25 |  | 934 | 952
Project Management | HSE Manager | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Project Management | HSE Manager | Plan (BAC) | R.14 - 9 Jun 25 |  | 505 | 505
Project Management | HSE Manager | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 505
Project Management | HSE Manager | Actual | R.14 - 9 Jun 25 |  | 505 | 505
Project Management | Other | Plan (Budget Award) | R.13 - 7 Jun 24
Project Management | Other | Plan (BAC) | R.14 - 9 Jun 25
Project Management | Other | Plan (EAC) | R.14 - 9 Jun 25
Project Management | Other | Actual | R.14 - 9 Jun 25
Project Management | Total for Project Management | Plan (Budget Award) | R.13 - 7 Jun 24
Project Management | Total for Project Management | Plan (BAC) | R.14 - 9 Jun 25
Project Management | Total for Project Management | Plan (EAC) | R.14 - 9 Jun 25
Project Management | Total for Project Management | Actual | R.14 - 9 Jun 25
Engineering | Project Engineering Mgr | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Project Engineering Mgr | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Project Engineering Mgr | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Project Engineering Mgr | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Structure | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Structure | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Structure | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Structure | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Piping | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Piping | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Piping | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Piping | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Instrument | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Instrument | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Instrument | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Instrument | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Electrical | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Electrical | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Electrical | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Electrical | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Civil | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Civil | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Civil | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Civil | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Mechanical | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Mechanical | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Mechanical | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Mechanical | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Process | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Process | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Process | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Process | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Safety | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Safety | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Safety | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Safety | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Document Control | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Document Control | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Document Control | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Document Control | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Strategic Planning | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 842
Engineering | Strategic Planning | Plan (BAC) | R.14 - 9 Jun 25 |  | 842 | 842
Engineering | Strategic Planning | Plan (EAC) | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Strategic Planning | Actual | R.14 - 9 Jun 25 |  | 842 | 859
Engineering | Other | Plan (Budget Award) | R.13 - 7 Jun 24
Engineering | Other | Plan (BAC) | R.14 - 9 Jun 25
Engineering | Other | Plan (EAC) | R.14 - 9 Jun 25
Engineering | Other | Actual | R.14 - 9 Jun 25
Engineering | Total for Engineering | Plan (Budget Award) | R.13 - 7 Jun 24
Engineering | Total for Engineering | Plan (BAC) | R.14 - 9 Jun 25
Engineering | Total for Engineering | Plan (EAC) | R.14 - 9 Jun 25
Engineering | Total for Engineering | Actual | R.14 - 9 Jun 25
Procurement | PPM | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 839 | 839
Procurement | PPM | Plan (BAC) | R.14 - 9 Jun 25 |  | 839 | 839
Procurement | PPM | Plan (EAC) | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | PPM | Actual | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Purchasing | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 839 | 839
Procurement | Purchasing | Plan (BAC) | R.14 - 9 Jun 25 |  | 839 | 839
Procurement | Purchasing | Plan (EAC) | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Purchasing | Actual | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Schedule and Scope | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 839 | 839
Procurement | Schedule and Scope | Plan (BAC) | R.14 - 9 Jun 25 |  | 839 | 839
Procurement | Schedule and Scope | Plan (EAC) | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Schedule and Scope | Actual | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | QC | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 839 | 839
Procurement | QC | Plan (BAC) | R.14 - 9 Jun 25 |  | 839 | 839
Procurement | QC | Plan (EAC) | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | QC | Actual | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Logistic | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 839 | 839
Procurement | Logistic | Plan (BAC) | R.14 - 9 Jun 25 |  | 839 | 839
Procurement | Logistic | Plan (EAC) | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Logistic | Actual | R.14 - 9 Jun 25 |  | 839 | 825
Procurement | Buyer | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Buyer | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Buyer | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Buyer | Actual | R.14 - 9 Jun 25
Procurement | Domestic | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Domestic | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Domestic | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Domestic | Actual | R.14 - 9 Jun 25
Procurement | Expedtor | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Expedtor | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Expedtor | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Expedtor | Actual | R.14 - 9 Jun 25
Procurement | Coordinator | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Coordinator | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Coordinator | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Coordinator | Actual | R.14 - 9 Jun 25
Procurement | Other | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Other | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Other | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Other | Actual | R.14 - 9 Jun 25
Procurement | Total for Procurement | Plan (Budget Award) | R.13 - 7 Jun 24
Procurement | Total for Procurement | Plan (BAC) | R.14 - 9 Jun 25
Procurement | Total for Procurement | Plan (EAC) | R.14 - 9 Jun 25
Procurement | Total for Procurement | Actual | R.14 - 9 Jun 25
Construction | Construction Manager | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Construction Manager | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Construction Manager | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Construction Manager | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Construction Engineer | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Construction Engineer | Plan (BAC) | R.14 - 9 Jun 25
Construction | Construction Engineer | Plan (EAC) | R.14 - 9 Jun 25
Construction | Construction Engineer | Actual | R.14 - 9 Jun 25
Construction | CSA | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | CSA | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | CSA | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | CSA | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Structural / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Structural / SV&A | Plan (BAC) | R.14 - 9 Jun 25
Construction | Structural / SV&A | Plan (EAC) | R.14 - 9 Jun 25
Construction | Structural / SV&A | Actual | R.14 - 9 Jun 25
Construction | Structural / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Structural / FM&B | Plan (BAC) | R.14 - 9 Jun 25
Construction | Structural / FM&B | Plan (EAC) | R.14 - 9 Jun 25
Construction | Structural / FM&B | Actual | R.14 - 9 Jun 25
Construction | Piping/Mechanical /SV&A | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Piping/Mechanical /SV&A | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Piping/Mechanical /SV&A | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Piping/Mechanical /SV&A | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Piping/Mechanical /FM&B | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Piping/Mechanical /FM&B | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Piping/Mechanical /FM&B | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Piping/Mechanical /FM&B | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Electrical/Instrument / SV&A | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / SV&A | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / SV&A | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Electrical/Instrument / FM&B | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / FM&B | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Electrical/Instrument / FM&B | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / SV&A | Plan (Budget Award) | R.12 - 19 Jun 23 |  | 580 | 610
Construction | Material Control / SV&A | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / SV&A | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / SV&A | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / FM&B | Plan (Budget Award) | R.12 - 19 Jun 23 |  | 580 | 610
Construction | Material Control / FM&B | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / FM&B | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Material Control / FM&B | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Blast & Paint / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Blast & Paint / SV&A | Plan (BAC) | R.14 - 9 Jun 25
Construction | Blast & Paint / SV&A | Plan (EAC) | R.14 - 9 Jun 25
Construction | Blast & Paint / SV&A | Actual | R.14 - 9 Jun 25
Construction | Blast & Paint / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Blast & Paint / FM&B | Plan (BAC) | R.14 - 9 Jun 25
Construction | Blast & Paint / FM&B | Plan (EAC) | R.14 - 9 Jun 25
Construction | Blast & Paint / FM&B | Actual | R.14 - 9 Jun 25
Construction | Project Operation Onshore | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Project Operation Onshore | Plan (BAC) | R.13 - 7 Jun 24 |  | 580 | 580
Construction | Project Operation Onshore | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Project Operation Onshore | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Project Operation Offshore | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Project Operation Offshore | Plan (BAC) | R.14 - 9 Jun 25
Construction | Project Operation Offshore | Plan (EAC) | R.14 - 9 Jun 25
Construction | Project Operation Offshore | Actual | R.14 - 9 Jun 25
Construction | QC / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Construction | QC / SV&A | Plan (BAC) | R.13 - 7 Jun 24 |  | 505 | 505
Construction | QC / SV&A | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QC / SV&A | Actual | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QC / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Construction | QC / FM&B | Plan (BAC) | R.13 - 7 Jun 24 |  | 505 | 505
Construction | QC / FM&B | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QC / FM&B | Actual | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QA / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Construction | QA / SV&A | Plan (BAC) | R.14 - 9 Jun 25 |  | 505 | 505
Construction | QA / SV&A | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QA / SV&A | Actual | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QA / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Construction | QA / FM&B | Plan (BAC) | R.14 - 9 Jun 25 |  | 505 | 505
Construction | QA / FM&B | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 533
Construction | QA / FM&B | Actual | R.14 - 9 Jun 25 |  | 505 | 533
Construction | Field Service | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Field Service | Plan (BAC) | R.13 - 7 Jun 24 |  | 580 | 580
Construction | Field Service | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Field Service | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Commissioning | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 580 | 610
Construction | Commissioning | Plan (BAC) | R.14 - 9 Jun 25 |  | 580 | 580
Construction | Commissioning | Plan (EAC) | R.14 - 9 Jun 25 |  | 580 | 699
Construction | Commissioning | Actual | R.14 - 9 Jun 25 |  | 580 | 699
Construction | HSE | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 505 | 501
Construction | HSE | Plan (BAC) | R.14 - 9 Jun 25 |  | 505 | 505
Construction | HSE | Plan (EAC) | R.14 - 9 Jun 25 |  | 505 | 533
Construction | HSE | Actual | R.14 - 9 Jun 25 |  | 505 | 533
Construction | Document Controller (Subcontractor) | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 188 | 188
Construction | Document Controller (Subcontractor) | Plan (BAC) | R.14 - 9 Jun 25
Construction | Document Controller (Subcontractor) | Plan (EAC) | R.14 - 9 Jun 25
Construction | Document Controller (Subcontractor) | Actual | R.14 - 9 Jun 25
Construction | Site Administrator (Subcontractor) | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 125 | 125
Construction | Site Administrator (Subcontractor) | Plan (BAC) | R.14 - 9 Jun 25
Construction | Site Administrator (Subcontractor) | Plan (EAC) | R.14 - 9 Jun 25
Construction | Site Administrator (Subcontractor) | Actual | R.14 - 9 Jun 25
Construction | Site Administrator | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 188 | 188
Construction | Site Administrator | Plan (BAC) | R.14 - 9 Jun 25
Construction | Site Administrator | Plan (EAC) | R.14 - 9 Jun 25
Construction | Site Administrator | Actual | R.14 - 9 Jun 25
Construction | Engineering | Plan (Budget Award) | R.13 - 7 Jun 24 |  | 842 | 859
Construction | Engineering | Plan (BAC) | R.13 - 7 Jun 24 |  | 842 | 859
Construction | Engineering | Plan (EAC) | R.13 - 7 Jun 24 |  | 842 | 859
Construction | Engineering | Actual | R.13 - 7 Jun 24 |  | 842 | 859
Construction | Procurement | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Procurement | Plan (BAC) | R.14 - 9 Jun 25
Construction | Procurement | Plan (EAC) | R.14 - 9 Jun 25
Construction | Procurement | Actual | R.14 - 9 Jun 25
Construction | PMT | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | PMT | Plan (BAC) | R.14 - 9 Jun 25
Construction | PMT | Plan (EAC) | R.14 - 9 Jun 25
Construction | PMT | Actual | R.14 - 9 Jun 25
Construction | Document Controller | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Document Controller | Plan (BAC) | R.14 - 9 Jun 25
Construction | Document Controller | Plan (EAC) | R.14 - 9 Jun 25
Construction | Document Controller | Actual | R.14 - 9 Jun 25
Construction | Total for Construction | Plan (Budget Award) | R.13 - 7 Jun 24
Construction | Total for Construction | Plan (BAC) | R.14 - 9 Jun 25
Construction | Total for Construction | Plan (EAC) | R.14 - 9 Jun 25
Construction | Total for Construction | Actual | R.14 - 9 Jun 25
HUC | Construction Engineer | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Construction Engineer | Plan (BAC) | R.14 - 9 Jun 25
HUC | Construction Engineer | Plan (EAC) | R.14 - 9 Jun 25
HUC | Construction Engineer | Actual | R.14 - 9 Jun 25
HUC | Structural / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Structural / SV&A | Plan (BAC) | R.14 - 9 Jun 25
HUC | Structural / SV&A | Plan (EAC) | R.14 - 9 Jun 25
HUC | Structural / SV&A | Actual | R.14 - 9 Jun 25
HUC | Structural / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Structural / FM&B | Plan (BAC) | R.14 - 9 Jun 25
HUC | Structural / FM&B | Plan (EAC) | R.14 - 9 Jun 25
HUC | Structural / FM&B | Actual | R.14 - 9 Jun 25
HUC | Electrical/Instrument / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Electrical/Instrument / SV&A | Plan (BAC) | R.14 - 9 Jun 25
HUC | Electrical/Instrument / SV&A | Plan (EAC) | R.14 - 9 Jun 25
HUC | Electrical/Instrument / SV&A | Actual | R.14 - 9 Jun 25
HUC | Electrical/Instrument / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Electrical/Instrument / FM&B | Plan (BAC) | R.14 - 9 Jun 25
HUC | Electrical/Instrument / FM&B | Plan (EAC) | R.14 - 9 Jun 25
HUC | Electrical/Instrument / FM&B | Actual | R.14 - 9 Jun 25
HUC | Blast & Paint / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Blast & Paint / SV&A | Plan (BAC) | R.14 - 9 Jun 25
HUC | Blast & Paint / SV&A | Plan (EAC) | R.14 - 9 Jun 25
HUC | Blast & Paint / SV&A | Actual | R.14 - 9 Jun 25
HUC | Blast & Paint / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Blast & Paint / FM&B | Plan (BAC) | R.14 - 9 Jun 25
HUC | Blast & Paint / FM&B | Plan (EAC) | R.14 - 9 Jun 25
HUC | Blast & Paint / FM&B | Actual | R.14 - 9 Jun 25
HUC | Project Operation Onshore | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Project Operation Onshore | Plan (BAC) | R.14 - 9 Jun 25
HUC | Project Operation Onshore | Plan (EAC) | R.14 - 9 Jun 25
HUC | Project Operation Onshore | Actual | R.14 - 9 Jun 25
HUC | Project Operation Offshore | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Project Operation Offshore | Plan (BAC) | R.14 - 9 Jun 25
HUC | Project Operation Offshore | Plan (EAC) | R.14 - 9 Jun 25
HUC | Project Operation Offshore | Actual | R.14 - 9 Jun 25
HUC | QC / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | QC / SV&A | Plan (BAC) | R.14 - 9 Jun 25
HUC | QC / SV&A | Plan (EAC) | R.14 - 9 Jun 25
HUC | QC / SV&A | Actual | R.14 - 9 Jun 25
HUC | QC / FM&B | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | QC / FM&B | Plan (BAC) | R.14 - 9 Jun 25
HUC | QC / FM&B | Plan (EAC) | R.14 - 9 Jun 25
HUC | QC / FM&B | Actual | R.14 - 9 Jun 25
HUC | QA / SV&A | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | QA / SV&A | Plan (BAC) | R.14 - 9 Jun 25
HUC | QA / SV&A | Plan (EAC) | R.14 - 9 Jun 25
HUC | QA / SV&A | Actual | R.14 - 9 Jun 25
HUC | Field Service | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Field Service | Plan (BAC) | R.14 - 9 Jun 25
HUC | Field Service | Plan (EAC) | R.14 - 9 Jun 25
HUC | Field Service | Actual | R.14 - 9 Jun 25
HUC | Commissioning | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Commissioning | Plan (BAC) | R.14 - 9 Jun 25
HUC | Commissioning | Plan (EAC) | R.14 - 9 Jun 25
HUC | Commissioning | Actual | R.14 - 9 Jun 25
HUC | HSE | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | HSE | Plan (BAC) | R.14 - 9 Jun 25
HUC | HSE | Plan (EAC) | R.14 - 9 Jun 25
HUC | HSE | Actual | R.14 - 9 Jun 25
HUC | Engineering | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Engineering | Plan (BAC) | R.14 - 9 Jun 25
HUC | Engineering | Plan (EAC) | R.14 - 9 Jun 25
HUC | Engineering | Actual | R.14 - 9 Jun 25
HUC | Procurement | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Procurement | Plan (BAC) | R.14 - 9 Jun 25
HUC | Procurement | Plan (EAC) | R.14 - 9 Jun 25
HUC | Procurement | Actual | R.14 - 9 Jun 25
HUC | PMT | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | PMT | Plan (BAC) | R.14 - 9 Jun 25
HUC | PMT | Plan (EAC) | R.14 - 9 Jun 25
HUC | PMT | Actual | R.14 - 9 Jun 25
HUC | Document Controller | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Document Controller | Plan (BAC) | R.14 - 9 Jun 25
HUC | Document Controller | Plan (EAC) | R.14 - 9 Jun 25
HUC | Document Controller | Actual | R.14 - 9 Jun 25
HUC | Site Administrator | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Site Administrator | Plan (BAC) | R.14 - 9 Jun 25
HUC | Site Administrator | Plan (EAC) | R.14 - 9 Jun 25
HUC | Site Administrator | Actual | R.14 - 9 Jun 25
HUC | Other | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Other | Plan (BAC) | R.14 - 9 Jun 25
HUC | Other | Plan (EAC) | R.14 - 9 Jun 25
HUC | Other | Actual | R.14 - 9 Jun 25
HUC | Total for HUC | Plan (Budget Award) | R.13 - 7 Jun 24
HUC | Total for HUC | Plan (BAC) | R.14 - 9 Jun 25
HUC | Total for HUC | Plan (EAC) | R.14 - 9 Jun 25
HUC | Total for HUC | Actual | R.14 - 9 Jun 25
Services To NSE | Overall | Plan (Budget Award) | R.13 - 7 Jun 24
Services To NSE | Overall | Plan (BAC) | R.14 - 9 Jun 25
Services To NSE | Overall | Plan (EAC) | R.14 - 9 Jun 25
Services To NSE | Overall | Actual | R.14 - 9 Jun 25
Services To NSE | Services To NSE | Plan (Budget Award) | R.13 - 7 Jun 24
Services To NSE | Services To NSE | Plan (BAC) | R.14 - 9 Jun 25
Services To NSE | Services To NSE | Plan (EAC) | R.14 - 9 Jun 25
Services To NSE | Services To NSE | Actual | R.14 - 9 Jun 25
Warranty Claim | Overall | Plan (Budget Award) | R.13 - 7 Jun 24
Warranty Claim | Overall | Plan (BAC) | R.14 - 9 Jun 25
Warranty Claim | Overall | Plan (EAC) | R.14 - 9 Jun 25
Warranty Claim | Overall | Actual | R.14 - 9 Jun 25
Warranty Claim | Warranty Claim | Plan (Budget Award) | R.13 - 7 Jun 24
Warranty Claim | Warranty Claim | Plan (BAC) | R.14 - 9 Jun 25
Warranty Claim | Warranty Claim | Plan (EAC) | R.14 - 9 Jun 25
Warranty Claim | Warranty Claim | Actual | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Overall | Plan (Budget Award) | R.13 - 7 Jun 24
Installation Campaign Deferment Recovery | Overall | Plan (BAC) | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Overall | Plan (EAC) | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Overall | Actual | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Installation Campaign Deferment Recovery | Plan (Budget Award) | R.13 - 7 Jun 24
Installation Campaign Deferment Recovery | Installation Campaign Deferment Recovery | Plan (BAC) | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Installation Campaign Deferment Recovery | Plan (EAC) | R.14 - 9 Jun 25
Installation Campaign Deferment Recovery | Installation Campaign Deferment Recovery | Actual | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Overall | Plan (Budget Award) | R.13 - 7 Jun 24
Offshore Carried Over Punch List Rectification | Overall | Plan (BAC) | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Overall | Plan (EAC) | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Overall | Actual | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Offshore Carried Over Punch List Rectification | Plan (Budget Award) | R.13 - 7 Jun 24
Offshore Carried Over Punch List Rectification | Offshore Carried Over Punch List Rectification | Plan (BAC) | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Offshore Carried Over Punch List Rectification | Plan (EAC) | R.14 - 9 Jun 25
Offshore Carried Over Punch List Rectification | Offshore Carried Over Punch List Rectification | Actual | R.14 - 9 Jun 25
Other | Overall | Plan (Budget Award) | R.13 - 7 Jun 24
Other | Overall | Plan (BAC) | R.14 - 9 Jun 25
Other | Overall | Plan (EAC) | R.14 - 9 Jun 25
Other | Overall | Actual | R.14 - 9 Jun 25
Other | Other | Plan (Budget Award) | R.13 - 7 Jun 24
Other | Other | Plan (BAC) | R.14 - 9 Jun 25
Other | Other | Plan (EAC) | R.14 - 9 Jun 25
Other | Other | Actual | R.14 - 9 Jun 25

## Validate_Empty
TRUE | TRUE | TRUE | TRUE
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11

## Validate_Value
NVARCHAR(255) | NVARCHAR(255) | NVARCHAR(255) | NVARCHAR(255) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2)
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11

## Configuration
col_number | range_start | range_stop | project_active_start | project_inactive_end | relate_document
2 | B10 | E? | 2024-01-01 | 2027-01-01

## Validate_Type (hidden)
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8
$B$2 | $C$2 | $D$2 | $E$2 | $F$2 | #REF! | $G$2 | $H$2
$B$3 | $C$3 | $D$3 | $E$3 | $F$3 | #REF! | $G$3 | $H$3
$B$4 | $C$4 | $D$4 | $E$4 | $F$4 | #REF! | $G$4 | $H$4
$B$5 | $C$5 | $D$5 | $E$5 | $F$5 | #REF! | $G$5 | $H$5
$B$6 | $C$6 | $D$6 | $E$6 | $F$6 | #REF! | $G$6 | $H$6
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | $F$10 | #REF!
|  |  |  | $F$11 | #REF!
|  |  |  | $F$12 | #REF!
|  |  |  | $F$13 | #REF!
|  |  |  | $F$14 | #REF!
|  |  |  | $F$15 | #REF!
|  |  |  | $F$16 | #REF!
|  |  |  | $F$17 | #REF!
|  |  |  | $F$18 | #REF!
|  |  |  | $F$19 | #REF!
|  |  |  | $F$20 | #REF!
|  |  |  | $F$21 | #REF!
|  |  |  | $F$22 | #REF!
|  |  |  | $F$23 | #REF!
|  |  |  | $F$24 | #REF!
|  |  |  | $F$25 | #REF!
|  |  |  | $F$26 | #REF!
|  |  |  | $F$27 | #REF!
|  |  |  | $F$28 | #REF!
|  |  |  | $F$29 | #REF!
|  |  |  | $F$30 | #REF!
|  |  |  | $F$31 | #REF!
|  |  |  | $F$32 | #REF!
|  |  |  | $F$33 | #REF!
|  |  |  | $F$34 | #REF! | $G$34 | $H$34
|  |  |  | $F$35 | #REF! | $G$35 | $H$35
|  |  |  | $F$36 | #REF! | $G$36 | $H$36
|  |  |  | $F$37 | #REF! | $G$37 | $H$37
|  |  |  | $F$38 | #REF! | $G$38 | $H$38
|  |  |  | $F$39 | #REF! | $G$39 | $H$39
|  |  |  | $F$40 | #REF! | $G$40 | $H$40
|  |  |  | $F$41 | #REF! | $G$41 | $H$41
|  |  |  | $F$42 | #REF!
|  |  |  | $F$43 | #REF!
|  |  |  | $F$44 | #REF!
|  |  |  | $F$45 | #REF!
|  |  |  | $F$46 | #REF!
|  |  |  | $F$47 | #REF!
|  |  |  | $F$48 | #REF!
|  |  |  | $F$49 | #REF!
|  |  |  | $F$50 | #REF!
|  |  |  | $F$51 | #REF!
|  |  |  | $F$52 | #REF!
|  |  |  | $F$53 | #REF!
|  |  |  | $F$54 | #REF!
|  |  |  | $F$55 | #REF!
|  |  |  | $F$56 | #REF!
|  |  |  | $F$57 | #REF!
|  |  |  | $F$58 | #REF!
|  |  |  | $F$59 | #REF!
|  |  |  | $F$60 | #REF!
|  |  |  | $F$61 | #REF!
|  |  |  | $F$62 | #REF!
|  |  |  | $F$63 | #REF!
|  |  |  | $F$64 | #REF!
|  |  |  | $F$65 | #REF!
|  |  |  | $F$66 | #REF!
|  |  |  | $F$67 | #REF!
|  |  |  | $F$68 | #REF!
|  |  |  | $F$69 | #REF!
|  |  |  | $F$70 | #REF!
|  |  |  | $F$71 | #REF!
|  |  |  | $F$72 | #REF!
|  |  |  | $F$73 | #REF!
|  |  |  | $F$74 | #REF!
|  |  |  | $F$75 | #REF!
|  |  |  | $F$76 | #REF!
|  |  |  | $F$77 | #REF!
|  |  |  | $F$78 | #REF!
|  |  |  | $F$79 | #REF!
|  |  |  | $F$80 | #REF!
|  |  |  | $F$81 | #REF!
|  |  |  | $F$82 | #REF!
|  |  |  | $F$83 | #REF!
|  |  |  | $F$84 | #REF!
|  |  |  | $F$85 | #REF!
|  |  |  | $F$86 | #REF! | $G$86 | $H$86
|  |  |  | $F$87 | #REF! | $G$87 | $H$87
|  |  |  | $F$88 | #REF! | $G$88 | $H$88
|  |  |  | $F$89 | #REF! | $G$89 | $H$89
|  |  |  | $F$90 | #REF! | $G$90 | $H$90
|  |  |  | $F$91 | #REF! | $G$91 | $H$91
|  |  |  | $F$92 | #REF! | $G$92 | $H$92
|  |  |  | $F$93 | #REF! | $G$93 | $H$93
|  |  |  | $F$94 | #REF!
|  |  |  | $F$95 | #REF!
|  |  |  | $F$96 | #REF!
|  |  |  | $F$97 | #REF!
|  |  |  | $F$98 | #REF!
|  |  |  | $F$99 | #REF!
|  |  |  | $F$100 | #REF!
|  |  |  | $F$101 | #REF!
|  |  |  | $F$102 | #REF!
|  |  |  | $F$103 | #REF!
|  |  |  | $F$104 | #REF!
|  |  |  | $F$105 | #REF!
|  |  |  | $F$106 | #REF!
|  |  |  | $F$107 | #REF!
|  |  |  | $F$108 | #REF!
|  |  |  | $F$109 | #REF!
|  |  |  | $F$110 | #REF!
|  |  |  | $F$111 | #REF!
|  |  |  | $F$112 | #REF!
|  |  |  | $F$113 | #REF!
|  |  |  | $F$114 | #REF! | $G$114 | $H$114
|  |  |  | $F$115 | #REF! | $G$115 | $H$115
|  |  |  | $F$116 | #REF! | $G$116 | $H$116
|  |  |  | $F$117 | #REF! | $G$117 | $H$117
|  |  |  | $F$118 | #REF! | $G$118 | $H$118
|  |  |  | $F$119 | #REF! | $G$119 | $H$119
|  |  |  | $F$120 | #REF! | $G$120 | $H$120
|  |  |  | $F$121 | #REF! | $G$121 | $H$121
|  |  |  | $F$122 | #REF! | $G$122 | $H$122
|  |  |  | $F$123 | #REF! | $G$123 | $H$123
|  |  |  | $F$124 | #REF! | $G$124 | $H$124
|  |  |  | $F$125 | #REF! | $G$125 | $H$125
|  |  |  | $F$126 | #REF! | $G$126 | $H$126
|  |  |  | $F$127 | #REF! | $G$127 | $H$127
|  |  |  | $F$128 | #REF! | $G$128 | $H$128
|  |  |  | $F$129 | #REF! | $G$129 | $H$129
|  |  |  | $F$130 | #REF! | $G$130 | $H$130
|  |  |  | $F$131 | #REF! | $G$131 | $H$131
|  |  |  | $F$132 | #REF! | $G$132 | $H$132
|  |  |  | $F$133 | #REF! | $G$133 | $H$133
|  |  |  | $F$134 | #REF! | $G$134 | $H$134
|  |  |  | $F$135 | #REF! | $G$135 | $H$135
|  |  |  | $F$136 | #REF! | $G$136 | $H$136
|  |  |  | $F$137 | #REF! | $G$137 | $H$137
|  |  |  | $F$138 | #REF!
|  |  |  | $F$139 | #REF!
|  |  |  | $F$140 | #REF!
|  |  |  | $F$141 | #REF!
|  |  |  | $F$142 | #REF! | $G$142 | $H$142
|  |  |  | $F$143 | #REF! | $G$143 | $H$143
|  |  |  | $F$144 | #REF! | $G$144 | $H$144
|  |  |  | $F$145 | #REF! | $G$145 | $H$145
|  |  |  | $F$146 | #REF!
|  |  |  | $F$147 | #REF!
|  |  |  | $F$148 | #REF!
|  |  |  | $F$149 | #REF!
|  |  |  | $F$150 | #REF! | $G$150 | $H$150
|  |  |  | $F$151 | #REF! | $G$151 | $H$151
|  |  |  | $F$152 | #REF! | $G$152 | $H$152
|  |  |  | $F$153 | #REF! | $G$153 | $H$153
|  |  |  | $F$154 | #REF! | $G$154 | $H$154
|  |  |  | $F$155 | #REF! | $G$155 | $H$155
|  |  |  | $F$156 | #REF! | $G$156 | $H$156
|  |  |  | $F$157 | #REF! | $G$157 | $H$157
|  |  |  | $F$158 | #REF!
|  |  |  | $F$159 | #REF!
|  |  |  | $F$160 | #REF!
|  |  |  | $F$161 | #REF!
|  |  |  | $F$162 | #REF!
|  |  |  | $F$163 | #REF!
|  |  |  | $F$164 | #REF!
|  |  |  | $F$165 | #REF!
|  |  |  | $F$166 | #REF!
|  |  |  | $F$167 | #REF!
|  |  |  | $F$168 | #REF!
|  |  |  | $F$169 | #REF!
|  |  |  | $F$170 | #REF!
|  |  |  | $F$171 | #REF!
|  |  |  | $F$172 | #REF!
|  |  |  | $F$173 | #REF!
|  |  |  | $F$174 | #REF!
|  |  |  | $F$175 | #REF!
|  |  |  | $F$176 | #REF!
|  |  |  | $F$177 | #REF!
|  |  |  | $F$178 | #REF!
|  |  |  | $F$179 | #REF!
|  |  |  | $F$180 | #REF!
|  |  |  | $F$181 | #REF!
|  |  |  | $F$182 | #REF! | $G$182 | $H$182
|  |  |  | $F$183 | #REF! | $G$183 | $H$183
|  |  |  | $F$184 | #REF! | $G$184 | $H$184
|  |  |  | $F$185 | #REF! | $G$185 | $H$185
|  |  |  | $F$186 | #REF! | $G$186 | $H$186
|  |  |  | $F$187 | #REF! | $G$187 | $H$187
|  |  |  | $F$188 | #REF! | $G$188 | $H$188
|  |  |  | $F$189 | #REF! | $G$189 | $H$189
|  |  |  | $F$190 | #REF!
|  |  |  | $F$191 | #REF!
|  |  |  | $F$192 | #REF!
|  |  |  | $F$193 | #REF!
|  |  |  | $F$194 | #REF! | $G$194 | $H$194
|  |  |  | $F$195 | #REF! | $G$195 | $H$195
|  |  |  | $F$196 | #REF! | $G$196 | $H$196
|  |  |  | $F$197 | #REF! | $G$197 | $H$197
|  |  |  | $F$198 | #REF!
|  |  |  | $F$199 | #REF!
|  |  |  | $F$200 | #REF!
|  |  |  | $F$201 | #REF!
|  |  |  | $F$202 | #REF!
|  |  |  | $F$203 | #REF!
|  |  |  | $F$204 | #REF!
|  |  |  | $F$205 | #REF!
|  |  |  | $F$206 | #REF!
|  |  |  | $F$207 | #REF!
|  |  |  | $F$208 | #REF!
|  |  |  | $F$209 | #REF!
|  |  |  | $F$210 | #REF!
|  |  |  | $F$211 | #REF!
|  |  |  | $F$212 | #REF!
|  |  |  | $F$213 | #REF!
|  |  |  | $F$214 | #REF!
|  |  |  | $F$215 | #REF!
|  |  |  | $F$216 | #REF!
|  |  |  | $F$217 | #REF!
|  |  |  | $F$218 | #REF!
|  |  |  | $F$219 | #REF!
|  |  |  | $F$220 | #REF!
|  |  |  | $F$221 | #REF!
|  |  |  | $F$222 | #REF!
|  |  |  | $F$223 | #REF!
|  |  |  | $F$224 | #REF!
|  |  |  | $F$225 | #REF!
|  |  |  | $F$226 | #REF!
|  |  |  | $F$227 | #REF! | $G$227 | $H$227
|  |  |  | $F$228 | #REF! | $G$228 | $H$228
|  |  |  | $F$229 | #REF! | $G$229 | $H$229
|  |  |  | $F$230 | #REF!
|  |  |  | $F$231 | #REF! | $G$231 | $H$231
|  |  |  | $F$232 | #REF! | $G$232 | $H$232
|  |  |  | $F$233 | #REF! | $G$233 | $H$233
|  |  |  | $F$234 | #REF!
|  |  |  | $F$235 | #REF! | $G$235 | $H$235
|  |  |  | $F$236 | #REF! | $G$236 | $H$236
|  |  |  | $F$237 | #REF! | $G$237 | $H$237
|  |  |  | $F$238 | #REF!
|  |  |  | $F$239 | #REF!
|  |  |  | $F$240 | #REF!
|  |  |  | $F$241 | #REF!
|  |  |  | $F$242 | #REF! | $G$242 | $H$242
|  |  |  | $F$243 | #REF! | $G$243 | $H$243
|  |  |  | $F$244 | #REF! | $G$244 | $H$244
|  |  |  | $F$245 | #REF! | $G$245 | $H$245
|  |  |  | $F$246 | #REF! | $G$246 | $H$246
|  |  |  | $F$247 | #REF! | $G$247 | $H$247
|  |  |  | $F$248 | #REF! | $G$248 | $H$248
|  |  |  | $F$249 | #REF! | $G$249 | $H$249
|  |  |  | $F$250 | #REF! | $G$250 | $H$250
|  |  |  | $F$251 | #REF! | $G$251 | $H$251
|  |  |  | $F$252 | #REF! | $G$252 | $H$252
|  |  |  | $F$253 | #REF! | $G$253 | $H$253
|  |  |  | $F$254 | #REF! | $G$254 | $H$254
|  |  |  | $F$255 | #REF! | $G$255 | $H$255
|  |  |  | $F$256 | #REF! | $G$256 | $H$256
|  |  |  | $F$257 | #REF! | $G$257 | $H$257
|  |  |  | $F$258 | #REF! | $G$258 | $H$258
|  |  |  | $F$259 | #REF! | $G$259 | $H$259
|  |  |  | $F$260 | #REF! | $G$260 | $H$260
|  |  |  | $F$261 | #REF! | $G$261 | $H$261
|  |  |  | $F$262 | #REF! | $G$262 | $H$262
|  |  |  | $F$263 | #REF! | $G$263 | $H$263
|  |  |  | $F$264 | #REF! | $G$264 | $H$264
|  |  |  | $F$265 | #REF! | $G$265 | $H$265
|  |  |  | $F$266 | #REF! | $G$266 | $H$266
|  |  |  | $F$267 | #REF! | $G$267 | $H$267
|  |  |  | $F$268 | #REF! | $G$268 | $H$268
|  |  |  | $F$269 | #REF! | $G$269 | $H$269
|  |  |  | $F$270 | #REF! | $G$270 | $H$270
|  |  |  | $F$271 | #REF! | $G$271 | $H$271
|  |  |  | $F$272 | #REF! | $G$272 | $H$272
|  |  |  | $F$273 | #REF! | $G$273 | $H$273
|  |  |  | $F$274 | #REF! | $G$274 | $H$274
|  |  |  | $F$275 | #REF! | $G$275 | $H$275
|  |  |  | $F$276 | #REF! | $G$276 | $H$276
|  |  |  | $F$277 | #REF! | $G$277 | $H$277
|  |  |  | $F$278 | #REF! | $G$278 | $H$278
|  |  |  | $F$279 | #REF! | $G$279 | $H$279
|  |  |  | $F$280 | #REF! | $G$280 | $H$280
|  |  |  | $F$281 | #REF! | $G$281 | $H$281
|  |  |  | $F$282 | #REF! | $G$282 | $H$282
|  |  |  | $F$283 | #REF! | $G$283 | $H$283
|  |  |  | $F$284 | #REF! | $G$284 | $H$284
|  |  |  | $F$285 | #REF! | $G$285 | $H$285
|  |  |  | $F$286 | #REF! | $G$286 | $H$286
|  |  |  | $F$287 | #REF! | $G$287 | $H$287
|  |  |  | $F$288 | #REF! | $G$288 | $H$288
|  |  |  | $F$289 | #REF! | $G$289 | $H$289
|  |  |  | $F$290 | #REF! | $G$290 | $H$290
|  |  |  | $F$291 | #REF! | $G$291 | $H$291
|  |  |  | $F$292 | #REF! | $G$292 | $H$292
|  |  |  | $F$293 | #REF! | $G$293 | $H$293
|  |  |  | $F$294 | #REF! | $G$294 | $H$294
|  |  |  | $F$295 | #REF! | $G$295 | $H$295
|  |  |  | $F$296 | #REF! | $G$296 | $H$296
|  |  |  | $F$297 | #REF! | $G$297 | $H$297
|  |  |  | $F$298 | #REF! | $G$298 | $H$298
|  |  |  | $F$299 | #REF! | $G$299 | $H$299
|  |  |  | $F$300 | #REF! | $G$300 | $H$300