## Raw Data
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13 | C14 | C15 | C16 | C17 | C18 | C19 | C20 | C21 | C22 | C23 | C24 | C25 | C26 | C27 | C28 | C29
QA001 | Overall Project | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 1 | 45536 | 0.03 | 0 | 0 | 0 | 402109.02 | 508493.02 | 910602.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402109.02 | 508493.02 | 910602.04 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 2 | 45566 | 0.11 | 0 | 402109.02 | 402109.02 | 859171.26 | 911124.69 | 1770295.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402109.02 | 402109.02 | 1261280.28 | 1419617.71 | 2680897.99 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 3 | 45597 | 0.19 | 0 | 859171.26 | 859171.26 | -1261280.28 | -1419617.71 | -2680897.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261280.28 | 1261280.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 4 | 45627 | 0.24 | 0 | 1400573.84 | 1400573.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2661854.12 | 2661854.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 5 | 45658 | 0.31 | 0 | 1582457.8 | 1582457.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244311.92 | 4244311.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 6 | 45689 | 0.46 | 0 | 1453772.75 | 1453772.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5698084.67 | 5698084.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 7 | 45717 | 0.62 | 0 | 2080094.71 | 2080094.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7778179.38 | 7778179.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 8 | 45748 | 0.78 | 0 | 1558161.19 | 1558161.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9336340.57 | 9336340.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 9 | 45778 | 0.79 | 0 | 1467853.71 | 1467853.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10804194.28 | 10804194.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 10 | 45809 | 0.82 | 0 | 1035421.42 | 1035421.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11839615.7 | 11839615.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 11 | 45839 | 0.87 | 0 | 1358709.9 | 1358709.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13198325.6 | 13198325.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 12 | 45870 | 0.92 | 0 | 701573.75 | 701573.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13899899.35 | 13899899.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 13 | 45901 | 0.94 | 0 | 678974.44 | 678974.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14578873.79 | 14578873.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 14 | 45931 | 0.95 | 0 | 583019.1 | 583019.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15161892.89 | 15161892.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 15 | 45962 | 0.98 | 0 | 715212.58 | 715212.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15877105.47 | 15877105.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 16 | 45992 | 1 | 0 | 755491.88 | 755491.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16632597.35 | 16632597.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 17 | 46023 | 1 | 0 | 218425.21 | 218425.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16851022.56 | 16851022.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 18 | 46054 | 1 | 0 | 75655.56 | 75655.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 19 | 46082 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 20 | 46113 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 21 | 46143 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 22 | 46174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 23 | 46204 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA001 | Overall Project | Month # 24 | 46235 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16926678.12 | 16926678.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
QAE001 | Engineering | Summary |  |  | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 | [14 empty] | 0 |  |  | 0
QAE001 | Engineering | Month # 1 | 45536 | 0.03 | 0 | 0 | 0 | 41258 | 41258 | 82516 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 41258 | 41258 | 82516 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 2 | 45566 | 0.42 | 0 | 41258 | 41258 | 302067.5 | 329126 | 631193.5 |  |  | 0 |  |  | 0 | 0 | 41258 | 41258 | 343325.5 | 370384 | 713709.5 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 3 | 45597 | 0.86 | 0 | 302067.5 | 302067.5 | -343325.5 | -370384 | -713709.5 |  |  | 0 |  |  | 0 | 0 | 343325.5 | 343325.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 4 | 45627 | 0.99 | 0 | 519025.64 | 519025.64 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 862351.14 | 862351.14 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 5 | 45658 | 1 | 0 | 667571.28 | 667571.28 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1529922.42 | 1529922.42 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 6 | 45689 | 1 | 0 | 528070.25 | 528070.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2057992.67 | 2057992.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 7 | 45717 | 1 | 0 | 760644.5 | 760644.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2818637.17 | 2818637.17 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 8 | 45748 | 1 | 0 | 467442.03 | 467442.03 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3286079.2 | 3286079.2 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 9 | 45778 | 1 | 0 | 111884.75 | 111884.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3397963.95 | 3397963.95 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 10 | 45809 | 1 | 0 | 37581.25 | 37581.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3435545.2 | 3435545.2 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 11 | 45839 | 1 | 0 | 91268.75 | 91268.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3526813.95 | 3526813.95 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 12 | 45870 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3526813.95 | 3526813.95 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 13 | 45901 | 1 | 0 | 3436 | 3436 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3530249.95 | 3530249.95 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 14 | 45931 | 1 | 0 | 30709.25 | 30709.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3560959.2 | 3560959.2 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 15 | 45962 | 1 | 0 | 61332.6 | 61332.6 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3622291.8 | 3622291.8 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 16 | 45992 | 1 | 0 | 170880.87 | 170880.87 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3793172.67 | 3793172.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 17 | 46023 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3793172.67 | 3793172.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 18 | 46054 | 1 | 0 | 15462 | 15462 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 19 | 46082 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 20 | 46113 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 21 | 46143 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 22 | 46174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 23 | 46204 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAE001 | Engineering | Month # 24 | 46235 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3808634.67 | 3808634.67 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Summary |  |  | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0
QAP001 | Procurement | Month # 1 | 45536 | 0 | 0 | 0 | 0 | 51665.62 | 51665.62 | 103331.24 | [6 empty] | 0 | 0 | 0 | 51665.62 | 51665.62 | 103331.24
QAP001 | Procurement | Month # 2 | 45566 | 0.2 | 0 | 51665.62 | 51665.62 | 225388.96 | 225388.96 | 450777.92 |  |  | 0 |  |  | 0 | 0 | 51665.62 | 51665.62 | 277054.58 | 277054.58 | 554109.16 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 3 | 45597 | 0.48 | 0 | 225388.96 | 225388.96 | -277054.58 | -277054.58 | -554109.16 |  |  | 0 |  |  | 0 | 0 | 277054.58 | 277054.58 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 4 | 45627 | 0.59 | 0 | 297870.17 | 297870.17 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 574924.75 | 574924.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 5 | 45658 | 0.75 | 0 | 361768.41 | 361768.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 936693.16 | 936693.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 6 | 45689 | 0.96 | 0 | 230628.75 | 230628.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1167321.91 | 1167321.91 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 7 | 45717 | 1 | 0 | 248234.25 | 248234.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1415556.16 | 1415556.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 8 | 45748 | 1 | 0 | 149118.75 | 149118.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1564674.91 | 1564674.91 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 9 | 45778 | 1 | 0 | 73210.5 | 73210.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1637885.41 | 1637885.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 10 | 45809 | 1 | 0 | 63747.75 | 63747.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1701633.16 | 1701633.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 11 | 45839 | 1 | 0 | 29213.25 | 29213.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1730846.41 | 1730846.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 12 | 45870 | 1 | 0 | 16021.5 | 16021.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1746867.91 | 1746867.91 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 13 | 45901 | 1 | 0 | 20691 | 20691 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1767558.91 | 1767558.91 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 14 | 45931 | 1 | 0 | 12853.5 | 12853.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1780412.41 | 1780412.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 15 | 45962 | 1 | 0 | 15807 | 15807 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1796219.41 | 1796219.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 16 | 45992 | 1 | 0 | 825 | 825 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1797044.41 | 1797044.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 17 | 46023 | 1 | 0 | 3918.75 | 3918.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 18 | 46054 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 19 | 46082 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 20 | 46113 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 21 | 46143 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 22 | 46174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 23 | 46204 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAP001 | Procurement | Month # 24 | 46235 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1800963.16 | 1800963.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Summary |  |  | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0
QAC001 | Construction | Month # 1 | 45536 | 0 | 0 | 0 | 0 | 5075 | 10025 | 15100 | [6 empty] | 0 | 0 | 0 | 5075 | 10025 | 15100
QAC001 | Construction | Month # 2 | 45566 | 0 | 0 | 5075 | 5075 | 47125 | 59630 | 106755 |  |  | 0 |  |  | 0 | 0 | 5075 | 5075 | 52200 | 69655 | 121855 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 3 | 45597 | 0 | 0 | 47125 | 47125 | -52200 | -69655 | -121855 |  |  | 0 |  |  | 0 | 0 | 52200 | 52200 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 4 | 45627 | 0.03 | 0 | 303786.25 | 303786.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 355986.25 | 355986.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 5 | 45658 | 0.09 | 0 | 306271.25 | 306271.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 662257.5 | 662257.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 6 | 45689 | 0.25 | 0 | 421135.75 | 421135.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1083393.25 | 1083393.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 7 | 45717 | 0.46 | 0 | 760778.28 | 760778.28 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1844171.53 | 1844171.53 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 8 | 45748 | 0.69 | 0 | 648784.25 | 648784.25 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2492955.78 | 2492955.78 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 9 | 45778 | 0.7 | 0 | 971273.58 | 971273.58 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3464229.36 | 3464229.36 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 10 | 45809 | 0.75 | 0 | 706659.62 | 706659.62 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 4170888.98 | 4170888.98 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 11 | 45839 | 0.81 | 0 | 975970.94 | 975970.94 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 5146859.92 | 5146859.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 12 | 45870 | 0.88 | 0 | 587334.41 | 587334.41 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 5734194.33 | 5734194.33 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 13 | 45901 | 0.92 | 0 | 552355.12 | 552355.12 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 6286549.45 | 6286549.45 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 14 | 45931 | 0.93 | 0 | 460630.75 | 460630.75 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 6747180.2 | 6747180.2 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 15 | 45962 | 0.97 | 0 | 519082.5 | 519082.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7266262.7 | 7266262.7 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 16 | 45992 | 1 | 0 | 499134.17 | 499134.17 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7765396.87 | 7765396.87 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 17 | 46023 | 1 | 0 | 134557.5 | 134557.5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7899954.37 | 7899954.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 18 | 46054 | 1 | 0 | 24465 | 24465 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 19 | 46082 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 20 | 46113 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 21 | 46143 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 22 | 46174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 23 | 46204 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAC001 | Construction | Month # 24 | 46235 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 7924419.37 | 7924419.37 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Summary |  |  | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0
QAM001 | Project Management | Month # 1 | 45536 | 0.64 | 0 | 0 | 0 | 304110.4 | 405544.4 | 709654.8 | [6 empty] | 0 | 0 | 0 | 304110.4 | 405544.4 | 709654.8
QAM001 | Project Management | Month # 2 | 45566 | 1 | 0 | 304110.4 | 304110.4 | 284589.8 | 296979.73 | 581569.53 |  |  | 0 |  |  | 0 | 0 | 304110.4 | 304110.4 | 588700.2 | 702524.13 | 1291224.33 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 3 | 45597 | 1 | 0 | 284589.8 | 284589.8 | -588700.2 | -702524.13 | -1291224.33 |  |  | 0 |  |  | 0 | 0 | 588700.2 | 588700.2 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 4 | 45627 | 1 | 0 | 279891.78 | 279891.78 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 868591.98 | 868591.98 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 5 | 45658 | 1 | 0 | 246846.86 | 246846.86 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1115438.84 | 1115438.84 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 6 | 45689 | 1 | 0 | 273938 | 273938 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1389376.84 | 1389376.84 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 7 | 45717 | 1 | 0 | 310437.68 | 310437.68 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1699814.52 | 1699814.52 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 8 | 45748 | 1 | 0 | 292816.16 | 292816.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 1992630.68 | 1992630.68 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 9 | 45778 | 1 | 0 | 311484.88 | 311484.88 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2304115.56 | 2304115.56 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 10 | 45809 | 1 | 0 | 227432.8 | 227432.8 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2531548.36 | 2531548.36 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 11 | 45839 | 1 | 0 | 262256.96 | 262256.96 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2793805.32 | 2793805.32 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 12 | 45870 | 1 | 0 | 98217.84 | 98217.84 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2892023.16 | 2892023.16 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 13 | 45901 | 1 | 0 | 102492.32 | 102492.32 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 2994515.48 | 2994515.48 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 14 | 45931 | 1 | 0 | 78825.6 | 78825.6 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3073341.08 | 3073341.08 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 15 | 45962 | 1 | 0 | 118990.48 | 118990.48 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3192331.56 | 3192331.56 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 16 | 45992 | 1 | 0 | 84651.84 | 84651.84 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3276983.4 | 3276983.4 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 17 | 46023 | 1 | 0 | 79948.96 | 79948.96 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3356932.36 | 3356932.36 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 18 | 46054 | 1 | 0 | 35728.56 | 35728.56 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 19 | 46082 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 20 | 46113 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 21 | 46143 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 22 | 46174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 23 | 46204 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
QAM001 | Project Management | Month # 24 | 46235 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 3392660.92 | 3392660.92 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0
N/A | HUC | Month # 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
N/A | HUC | Month # 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | HUC | Month # 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Offshore Carried Over Punch List Rectification | Month # 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0
N/A | Services To NSE | Month # 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
N/A | Services To NSE | Month # 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Services To NSE | Month # 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
N/A | Subcontract To NSE | Month # 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Subcontract To NSE | Month # 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Summary |  |  | 0 | 0 | 0 | 0 | 0 | 0
N/A | Warranty Claim | Month # 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
N/A | Warranty Claim | Month # 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0
N/A | Warranty Claim | Month # 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0

## Validate_Empty
TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13 | C14 | C15 | C16 | C17 | C18 | C19 | C20 | C21 | C22 | C23 | C24 | C25 | C26 | C27 | C28 | C29
$B$260 | $C$260
$B$261 | $C$261
$B$262 | $C$262
$B$263 | $C$263
$B$264 | $C$264
$B$265 | $C$265
$B$266 | $C$266
$B$267 | $C$267
$B$268 | $C$268
$B$269 | $C$269
$B$270 | $C$270
$B$271 | $C$271
$B$272 | $C$272
$B$273 | $C$273
$B$274 | $C$274
$B$275 | $C$275
$B$276 | $C$276
$B$277 | $C$277
$B$278 | $C$278
$B$279 | $C$279
$B$280 | $C$280
$B$281 | $C$281
$B$282 | $C$282
$B$283 | $C$283
$B$284 | $C$284
$B$285 | $C$285
$B$286 | $C$286
$B$287 | $C$287
$B$288 | $C$288
$B$289 | $C$289
$B$290 | $C$290
$B$291 | $C$291
$B$292 | $C$292
$B$293 | $C$293
$B$294 | $C$294
$B$295 | $C$295

## Validate_Value
NVARCHAR(20) | NVARCHAR(255) | NVARCHAR(20) | DATE | DECIMAL(13,2) [Percentage] | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2) | DECIMAL(13,2)
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13 | C14 | C15 | C16 | C17 | C18 | C19 | C20 | C21 | C22 | C23 | C24 | C25 | C26 | C27 | C28 | C29

## Validate_Condition
| Yes | Yes
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C13 | C14 | C15 | C16 | C17 | C18 | C19 | C20 | C21 | C22 | C23 | C24 | C25 | C26 | C27 | C28 | C29

## Configuration
col_number | range_start | range_stop | project_active_start | project_inactive_end | relate_document
2 | B10 | AD? | 2024-01-01 | 2027-01-01

## Validate_Type (hidden)
C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8
$B$2 | $C$2 | $D$2 | $E$2 | $F$2 | #REF! | $G$2 | $H$2
$B$3 | $C$3 | $D$3 | $E$3 | $F$3 | #REF! | $G$3 | $H$3
$B$4 | $C$4 | $D$4 | $E$4 | $F$4 | #REF! | $G$4 | $H$4
$B$5 | $C$5 | $D$5 | $E$5 | $F$5 | #REF! | $G$5 | $H$5
$B$6 | $C$6 | $D$6 | $E$6 | $F$6 | #REF! | $G$6 | $H$6
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | $E$10 | $F$10 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  |  | $E$35 | $F$35 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  |  | $E$60 | $F$60 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  |  | $E$85 | $F$85 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  |  | $E$110 | $F$110 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  |  | $E$135 | $F$135 | #REF!
|  |  | $E$136 | $F$136 | #REF!
|  |  | $E$137 | $F$137 | #REF!
|  |  | $E$138 | $F$138 | #REF!
|  |  | $E$139 | $F$139 | #REF!
|  |  | $E$140 | $F$140 | #REF!
|  |  | $E$141 | $F$141 | #REF!
|  |  | $E$142 | $F$142 | #REF!
|  |  | $E$143 | $F$143 | #REF!
|  |  | $E$144 | $F$144 | #REF!
|  |  | $E$145 | $F$145 | #REF!
|  |  | $E$146 | $F$146 | #REF!
|  |  | $E$147 | $F$147 | #REF!
|  |  | $E$148 | $F$148 | #REF!
|  |  | $E$149 | $F$149 | #REF!
|  |  | $E$150 | $F$150 | #REF!
|  |  | $E$151 | $F$151 | #REF!
|  |  | $E$152 | $F$152 | #REF!
|  |  | $E$153 | $F$153 | #REF!
|  |  | $E$154 | $F$154 | #REF!
|  |  | $E$155 | $F$155 | #REF!
|  |  | $E$156 | $F$156 | #REF!
|  |  | $E$157 | $F$157 | #REF!
|  |  | $E$158 | $F$158 | #REF!
|  |  | $E$159 | $F$159 | #REF!
|  |  | $E$160 | $F$160 | #REF!
|  |  | $E$161 | $F$161 | #REF!
|  |  | $E$162 | $F$162 | #REF!
|  |  | $E$163 | $F$163 | #REF!
|  |  | $E$164 | $F$164 | #REF!
|  |  | $E$165 | $F$165 | #REF!
|  |  | $E$166 | $F$166 | #REF!
|  |  | $E$167 | $F$167 | #REF!
|  |  | $E$168 | $F$168 | #REF!
|  |  | $E$169 | $F$169 | #REF!
|  |  | $E$170 | $F$170 | #REF!
|  |  | $E$171 | $F$171 | #REF!
|  |  | $E$172 | $F$172 | #REF!
|  |  | $E$173 | $F$173 | #REF!
|  |  | $E$174 | $F$174 | #REF!
|  |  | $E$175 | $F$175 | #REF!
|  |  | $E$176 | $F$176 | #REF!
|  |  | $E$177 | $F$177 | #REF!
|  |  | $E$178 | $F$178 | #REF!
|  |  | $E$179 | $F$179 | #REF!
|  |  | $E$180 | $F$180 | #REF!
|  |  | $E$181 | $F$181 | #REF!
|  |  | $E$182 | $F$182 | #REF!
|  |  | $E$183 | $F$183 | #REF!
|  |  | $E$184 | $F$184 | #REF!
|  |  | $E$185 | $F$185 | #REF!
|  |  | $E$186 | $F$186 | #REF!
|  |  | $E$187 | $F$187 | #REF!
|  |  | $E$188 | $F$188 | #REF!
|  |  | $E$189 | $F$189 | #REF!
|  |  | $E$190 | $F$190 | #REF!
|  |  | $E$191 | $F$191 | #REF!
|  |  | $E$192 | $F$192 | #REF!
|  |  | $E$193 | $F$193 | #REF!
|  |  | $E$194 | $F$194 | #REF!
|  |  | $E$195 | $F$195 | #REF!
|  |  | $E$196 | $F$196 | #REF!
|  |  | $E$197 | $F$197 | #REF!
|  |  | $E$198 | $F$198 | #REF!
|  |  | $E$199 | $F$199 | #REF!
|  |  | $E$200 | $F$200 | #REF!
|  |  | $E$201 | $F$201 | #REF!
|  |  | $E$202 | $F$202 | #REF!
|  |  | $E$203 | $F$203 | #REF!
|  |  | $E$204 | $F$204 | #REF!
|  |  | $E$205 | $F$205 | #REF!
|  |  | $E$206 | $F$206 | #REF!
|  |  | $E$207 | $F$207 | #REF!
|  |  | $E$208 | $F$208 | #REF!
|  |  | $E$209 | $F$209 | #REF!
|  |  | $E$210 | $F$210 | #REF!
|  |  | $E$211 | $F$211 | #REF!
|  |  | $E$212 | $F$212 | #REF!
|  |  | $E$213 | $F$213 | #REF!
|  |  | $E$214 | $F$214 | #REF!
|  |  | $E$215 | $F$215 | #REF!
|  |  | $E$216 | $F$216 | #REF!
|  |  | $E$217 | $F$217 | #REF!
|  |  | $E$218 | $F$218 | #REF!
|  |  | $E$219 | $F$219 | #REF!
|  |  | $E$220 | $F$220 | #REF!
|  |  | $E$221 | $F$221 | #REF!
|  |  | $E$222 | $F$222 | #REF!
|  |  | $E$223 | $F$223 | #REF!
|  |  | $E$224 | $F$224 | #REF!
|  |  | $E$225 | $F$225 | #REF!
|  |  | $E$226 | $F$226 | #REF!
|  |  | $E$227 | $F$227 | #REF!
|  |  | $E$228 | $F$228 | #REF!
|  |  | $E$229 | $F$229 | #REF!
|  |  | $E$230 | $F$230 | #REF!
|  |  | $E$231 | $F$231 | #REF!
|  |  | $E$232 | $F$232 | #REF!
|  |  | $E$233 | $F$233 | #REF!
|  |  | $E$234 | $F$234 | #REF!
|  |  | $E$235 | $F$235 | #REF!
|  |  | $E$236 | $F$236 | #REF!
|  |  | $E$237 | $F$237 | #REF!
|  |  | $E$238 | $F$238 | #REF!
|  |  | $E$239 | $F$239 | #REF!
|  |  | $E$240 | $F$240 | #REF!
|  |  | $E$241 | $F$241 | #REF!
|  |  | $E$242 | $F$242 | #REF!
|  |  | $E$243 | $F$243 | #REF!
|  |  | $E$244 | $F$244 | #REF!
|  |  | $E$245 | $F$245 | #REF!
|  |  | $E$246 | $F$246 | #REF!
|  |  | $E$247 | $F$247 | #REF!
|  |  | $E$248 | $F$248 | #REF!
|  |  | $E$249 | $F$249 | #REF!
|  |  | $E$250 | $F$250 | #REF!
|  |  | $E$251 | $F$251 | #REF!
|  |  | $E$252 | $F$252 | #REF!
|  |  | $E$253 | $F$253 | #REF!
|  |  | $E$254 | $F$254 | #REF!
|  |  | $E$255 | $F$255 | #REF!
|  |  | $E$256 | $F$256 | #REF!
|  |  | $E$257 | $F$257 | #REF!
|  |  | $E$258 | $F$258 | #REF!
|  |  | $E$259 | $F$259 | #REF!
$B$260 | $C$260 | $D$260 | $E$260 | $F$260 | #REF! | $G$260 | $H$260
$B$261 | $C$261 | $D$261 | $E$261 | $F$261 | #REF! | $G$261 | $H$261
$B$262 | $C$262 | $D$262 | $E$262 | $F$262 | #REF! | $G$262 | $H$262
$B$263 | $C$263 | $D$263 | $E$263 | $F$263 | #REF! | $G$263 | $H$263
$B$264 | $C$264 | $D$264 | $E$264 | $F$264 | #REF! | $G$264 | $H$264
$B$265 | $C$265 | $D$265 | $E$265 | $F$265 | #REF! | $G$265 | $H$265
$B$266 | $C$266 | $D$266 | $E$266 | $F$266 | #REF! | $G$266 | $H$266
$B$267 | $C$267 | $D$267 | $E$267 | $F$267 | #REF! | $G$267 | $H$267
$B$268 | $C$268 | $D$268 | $E$268 | $F$268 | #REF! | $G$268 | $H$268
$B$269 | $C$269 | $D$269 | $E$269 | $F$269 | #REF! | $G$269 | $H$269
$B$270 | $C$270 | $D$270 | $E$270 | $F$270 | #REF! | $G$270 | $H$270
$B$271 | $C$271 | $D$271 | $E$271 | $F$271 | #REF! | $G$271 | $H$271
$B$272 | $C$272 | $D$272 | $E$272 | $F$272 | #REF! | $G$272 | $H$272
$B$273 | $C$273 | $D$273 | $E$273 | $F$273 | #REF! | $G$273 | $H$273
$B$274 | $C$274 | $D$274 | $E$274 | $F$274 | #REF! | $G$274 | $H$274
$B$275 | $C$275 | $D$275 | $E$275 | $F$275 | #REF! | $G$275 | $H$275
$B$276 | $C$276 | $D$276 | $E$276 | $F$276 | #REF! | $G$276 | $H$276
$B$277 | $C$277 | $D$277 | $E$277 | $F$277 | #REF! | $G$277 | $H$277
$B$278 | $C$278 | $D$278 | $E$278 | $F$278 | #REF! | $G$278 | $H$278
$B$279 | $C$279 | $D$279 | $E$279 | $F$279 | #REF! | $G$279 | $H$279
$B$280 | $C$280 | $D$280 | $E$280 | $F$280 | #REF! | $G$280 | $H$280
$B$281 | $C$281 | $D$281 | $E$281 | $F$281 | #REF! | $G$281 | $H$281
$B$282 | $C$282 | $D$282 | $E$282 | $F$282 | #REF! | $G$282 | $H$282
$B$283 | $C$283 | $D$283 | $E$283 | $F$283 | #REF! | $G$283 | $H$283
$B$284 | $C$284 | $D$284 | $E$284 | $F$284 | #REF! | $G$284 | $H$284
$B$285 | $C$285 | $D$285 | $E$285 | $F$285 | #REF! | $G$285 | $H$285
$B$286 | $C$286 | $D$286 | $E$286 | $F$286 | #REF! | $G$286 | $H$286
$B$287 | $C$287 | $D$287 | $E$287 | $F$287 | #REF! | $G$287 | $H$287
$B$288 | $C$288 | $D$288 | $E$288 | $F$288 | #REF! | $G$288 | $H$288
$B$289 | $C$289 | $D$289 | $E$289 | $F$289 | #REF! | $G$289 | $H$289
$B$290 | $C$290 | $D$290 | $E$290 | $F$290 | #REF! | $G$290 | $H$290
$B$291 | $C$291 | $D$291 | $E$291 | $F$291 | #REF! | $G$291 | $H$291
$B$292 | $C$292 | $D$292 | $E$292 | $F$292 | #REF! | $G$292 | $H$292
$B$293 | $C$293 | $D$293 | $E$293 | $F$293 | #REF! | $G$293 | $H$293
$B$294 | $C$294 | $D$294 | $E$294 | $F$294 | #REF! | $G$294 | $H$294
$B$295 | $C$295 | $D$295 | $E$295 | $F$295 | #REF! | $G$295 | $H$295
$B$296 | $C$296 | $D$296 | $E$296 | $F$296 | #REF! | $G$296 | $H$296
$B$297 | $C$297 | $D$297 | $E$297 | $F$297 | #REF! | $G$297 | $H$297
$B$298 | $C$298 | $D$298 | $E$298 | $F$298 | #REF! | $G$298 | $H$298
$B$299 | $C$299 | $D$299 | $E$299 | $F$299 | #REF! | $G$299 | $H$299
$B$300 | $C$300 | $D$300 | $E$300 | $F$300 | #REF! | $G$300 | $H$300